## Production Schedule
JOB | [15 empty] | PROCESSING | PRODUCTION |  |  |  | 1 |  | 5 | 1 |  | 1 | 1 | 0 | 0 | 1 |  |  |  | Days
DO NOT DELETE ROWS FROM SHEET PLEASE. HIGHLIGHT THE LINE AND DELETE THE CONTENTS ONLY. THANKS. ML | TYPE | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | MSD - Measured CAD - Drawings Comp MTO - Material Takeoff PS - Production Sheets Comp ORD - Ordered from PC | Status | Date Req | Scheduled Date | Notes | Picked | To PC | From PC | Cut | Pinned | Prep | Assem bled | Hinging | Packup | QC | Disp | Invoice # | Panels # | Days
Samples Dli & CL |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Make from current material | deduct clips, pivots etc |  |  | DO NOT INCLUDE IN WEEKLY SORTING | 2017-05-09 | 2017-05-09 | 2017-05-15 | 2017-05-16 | 2017-05-18 | 2017-05-17 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-20 | 2017-05-20
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Grand Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WHOLESALE/RETAIL JOBS |  |  |  | 0
Sq Mtrs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | PANELS |  |  |  | 0
Commercial Panels
Commercial SQM | [15 empty] | SQUARE METRES |  |  |  | 0
Domestic Panels |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | COMMERCIAL JOBS |  |  |  | 0
Domestic SQM |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dli
DL
CL
EXT
FSH

## Production Completed
JOB | [15 empty] | PROCESSING | PRODUCTION |  |  | 49 |  | 22 | 44.9% | Percentage Processed | 1 |  | 5 | 1 | 1 |  | 1 | 0 | 1 |  |  |  |  | Days
DO NOT DELETE ROWS FROM SHEET PLEASE. HIGHLIGHT THE LINE AND DELETE THE CONTENTS ONLY. THANKS. ML | TYPE | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | MSD - Measured CAD - Drawings Comp MTO - Material Takeoff PS - Production Sheets Comp ORD - Ordered from PC | Status | Date Req | Notes | [5 empty] | Picked | To PC | From PC | Cut | Prep | Pinned | Assem bled | Packup | QC | Disp | Invoice # | Est. | Panels # | Days
A to Z Security - 2616 | CL | 2017-06-12: 29 |  |  |  | 36.2 | [9 empty] | PS 4/5 ORD 5/5 | YATES | 2017-05-04 | 2017-06-21 | White satin. Needing profile, will PC MILL asap. Profile arrived 5/6. To dispatch 12/6. Completed 15/6. & 21/6 | 14 |  |  |  | 2017-06-21 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-21 | 2017-06-22 |  | 29
Advanced Aussie - Walker - 2695
Advanced Aussie - Walker - 2695 | DLi | 2017-06-12: 3 |  |  |  | 2.3 | [9 empty] | MTO 18/5 - PS 7/6 | KRISTOM / BUSHLAND | 2017-06-09 | 2017-06-27 | Est 15/6. Est 26/6. Est 27/6. Completed 27/6 | 24 |  |  |  | 2017-06-23 | 2017-05-31 | 2017-05-31 | 2017-05-31 | [6 empty] | 3
All Seasons - Lange - 2716 | DLi | 2017-06-12: 5 |  | 6.8 | [5 empty] | PS 1/6 CF | ANODIC SIL GRY | 2017-06-17 | PAPERWORK MISSING | 34 |  | 1 |  |  | 2017-06-15 | 2017-06-15 | 2017-06-15 | [10 empty] | 5
Alroe Cons - 10497 RETAIL | DLi | 2017-06-12: 14 | 18.8 | [6 empty] | PS, CAD 11/05 - ORD 12/05 | MONUMENT | 2017-05-15 | FLASHINGS FROM P&J, YATES TO PC. Profile due am 31/5/17. Profile arrived, quality bad, need more. Due back 7/6. New profile sending 13/6. Due for install Friday 13/6. Completed 15/6 | 13 | [9 empty] | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 |  |  | 2017-06-16 | 14
Apollo - Atkins - 2663 | DLi | 2017-06-12: 2 |  |  |  | 3.7 | [9 empty] | PS 11/5 | SURFMIST | 2017-05-07 | 2017-06-15 | TM5, AS8c & L FRAME TO YATES. Completed 1/6 | 7 |  |  |  | 2017-05-30 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 |  | 2
Bayside RS - 2718 | DLi | [7 empty] | 2.2 | [6 empty] | PS 9/6 | PEARL WHITE | 2017-06-17 |  | 27 |  |  | 2017-05-26 | [17 empty] | 1 | bar: 2017-06-12
Blindo - Elements u25 - 2720 | DLI | 2017-06-12: 9 |  | 9 | [5 empty] | PS 12/6 - ORD 14/6 | SURFMIST | 2017-06-19 | Waiting on box. Est 22/6 | 36 | [6 empty] | 2017-06-21 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-14 | [5 empty] | 2017-06-22 | 9
Blindo - Elements u25 - 2720 | DLI | 2017-06-12: 9 |  |  |  | 9 | [9 empty] | PS 12/6 - ORD 14/6 | SURFMIST | 2017-06-19 | 2017-06-22 | Waiting on box. Est 22/6. Completed 22/6 | 17 |  |  |  | 2017-06-21 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-14 | 2017-06-22 | 2017-06-22 | 2017-06-22 |  |  | 9
Boardwalk - Parlevliet - 2682
Boardwalk - Bateman - 2711 | DLi | 2017-06-12: 10 | 9.6 | [6 empty] | PS 1/6 AF | PEARL WHITE | 2017-06-17 |  | 34 |  | 1 |  |  |  |  | 2017-06-15 | [9 empty] | 2017-06-16 | 10
Boardwalk - Bateman - 2711 | DLi | 2017-06-12: 10 |  |  |  | 9.6 | [9 empty] | PS 1/6 AF | PEARL WHITE | 2017-06-17 | 2017-06-22 |  | 16 |  |  |  | 2017-05-30 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-07 | 2017-06-07 | 2017-06-07 |  |  | 10
Boardwalk - Carvalho - 2725 | Dli | 2017-06-12: 11 |  |  |  | 16.2 | [9 empty] | PS 16/6 | PEARL WHITE | 2017-06-19 | 2017-06-28 | est28/6 | 26 |  |  |  | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 |  | 11
Boardwalk - Cummings 1 - 2728 | DLi | 2017-06-19: 16 |  | 12.7 | [5 empty] | PS 13/6 | PEARL WHITE | 2017-06-19 | DESPATCH WITH 2729 & 2730. Completed 16/6 | 43 | [5 empty] | 2017-05-23 | 2017-05-30 | 2017-06-12 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 |  | 2017-06-16 | 16
Boardwalk - Cummings 2 - 2729 | DLi | 2017-06-19: 16 |  | 23 | [5 empty] | PS 12/6 | PEARL WHITE | 2017-06-19 | DESPATCH WITH 2728 & 2730. Completed 16/6 | 42 | [6 empty] | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 |  | 2017-06-16 | 16
Boardwalk - Cummings 2 - 2729 | DLi | 2017-06-12: 16 |  |  |  | 23 | [9 empty] | PS 12/6 | PEARL WHITE | 2017-06-19 | 2017-06-16 | DESPATCH WITH 2728 & 2730. Completed 16/6 | 11 |  |  | 2017-05-26 | 2017-06-20 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 |  |  | 16
Boardwalk - Cummings 3 - 2730 | Dli | 2017-06-19: 16 |  | 12.2 | [5 empty] | PS 12/6 | PEARL WHITE | 2017-06-19 | DESPATCH WITH 2729 &2728. Completed 16/6 | 39 | [6 empty] | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 | 2017-06-16 |  | 2017-06-16 | 16
Boardwalk - Cummings 3 - 2730 | Dli | 2017-06-12: 16 |  |  |  | 12.2 | [9 empty] | PS 12/6 | PEARL WHITE | 2017-06-19 | 2017-06-16 | DESPATCH WITH 2729 &2728. Completed 16/6 | 10 |  |  | 2017-05-25 | 2017-06-09 | 2017-06-02 | 2017-06-02 | 2017-06-02 | 2017-06-02 | 2017-06-02 | 2017-06-02 | 2017-06-02 | 2017-06-02 |  | 16
Boardwalk - Dillon - 2724 | DLi | 2017-06-12: 8 |  |  |  | 16.3 | [9 empty] | PS 16/6 | YATES/Citi Matt | 2017-06-30 | 2017-06-30 | Est 29/6 | 49 |  |  |  | 2017-06-22 | [9 empty] | 8
Boardwalk - Fudge3 - 2710 | DLi | 2017-06-12: 16 | 9.8 | [6 empty] | PS 1/6 AF | PEARL WHITE | 2017-06-17 |  | 35 | [6 empty] | 2017-06-01 | 2017-05-30 | 2017-05-30 | 2017-05-30 |  |  |  | 2017-05-30 |  |  | 2017-06-09 | 16
Boardwalk - Gregory - 2805 | DLi | 2017-06-19: 6 |  |  | 4.4 | [6 empty] | PS 6/7 - AF | MONUMENT | 2017-07-20 |  |  | 54 | [12 empty] | 6
Boardwalk - Hickey - 2726 | DLi | 2017-06-12: 26 |  |  |  | 20.8 | [9 empty] | PS 1/6 AF | WHITE SATIN | 2017-06-19 | 2017-06-28 | Est 27/6. est 3/7 | 27 |  | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | [7 empty] | 26
Boardwalk - Hodginson - 2737 | DLi | 2017-06-12: 6 |  | 9.1 | [7 empty] | PS 21/6 | PEARL WHITE | 2017-06-25 | 2017-07-11 |  | 13 | [12 empty] | 6
Boardwalk - Mahoney - 2723 | DLi | 2017-06-12: 6 |  |  |  | 6.9 | [9 empty] | PS20/6 | yates/Basalt | 2017-06-03 | 2017-06-09 | date wrong returned to Robyn | 6 |  |  |  | 2017-06-07 | 2017-06-05 | 2017-06-05 | 2017-06-05 | [6 empty] | 6
Boardwalk - Sims - 2751 | DLi | 2017-06-12: 8 |  |  |  | 11.8 | [9 empty] | PS 6/6 AF | PEARL WHITE | 2017-06-29 | 2017-06-29 | est 29/6. Completed 27/6 | 49 |  | 2017-06-20 | 2017-06-20 | 2017-06-20 | [9 empty] | 8
Bozzy - Biglin - 2592 | DLi | 2017-06-12: 10 | 9.6 | [6 empty] | MTO 18/4, PS 09/05 | YATES | 2017-04-24 | Waiting 150 PROFILE from PC. Back from PC 28/4. PC quality - new 150 due back 7/6. Blades failed QC 7/6. To dispatch 9/6. PC issues, new profile to be done. | 6 |  | 1 |  |  |  |  | 2017-04-28 | 2017-06-12 | 2017-06-12 | 2017-06-12 | [5 empty] | 2017-06-16 | 10
Bozzy - Dudney - 2704 | DLi | 2017-06-12: 8 |  |  |  | 11 .5 | [9 empty] | PS 31/5 AF | SURFMIST | 2017-06-04 | 2017-06-20 | Completed 15/6 | 12 |  |  |  | 2017-05-29 | 2017-06-07 | 2017-06-12 | 2017-06-07 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-16 | 2017-06-20 |  | 8
Bozzy - Heighton - 2761 | DLi | 2017-06-12: 6 |  |  | 3.4 | [8 empty] | PS 28/6 | WHITE SATIN | 2017-06-27 | 2017-07-07 |  | 17 |  |  | 2017-06-09 | [9 empty] | 6
Bozzy - Lumbus - 2666 | DLi | 2017-06-12: 6 | 7.4 | [6 empty] | MTO 18/4 PS 16/5 | YATES | 2017-05-22 | JM to confirm date back from PC 30/5. Due back 31/5 Allan, if back 31/5 then done Thursday. Returned 1/6. to dispatch 9/6 | 20 |  | 1 |  |  |  |  | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 |  |  | 2017-06-15 | 6
Bozzy - Metcalf - 2800 | DLi | 2017-06-26: 2 |  |  |  |  | 2 | [6 empty] | PS 06/07 - AF | MONUMENT | 2017-07-17 |  |  | 52 | [12 empty] | 2
Bozzy - Ruzich - 2739 | DLi | 2017-06-12: 6 |  |  | 7.4 | [8 empty] | PS 7/6 | CUSTOM BLACK | 2017-06-25 | 2017-06-30 | URGENT ORDER | 35 | [13 empty] | 6
City Gate - Maguire Recto - RM2602 | DLi | 2017-06-12: 2 |  |  | 1.9 | [8 empty] | PS 26/6 | YATES/PALLADIUM SILVER PRL | ASAP | 2017-06-01 | MISALIGNED HINGING AND SCRATCHES ON BLADES | 3
Clough - 11391 RETAIL | DLi | 2017-06-12: 8 |  |  |  | 15.4 | [9 empty] | PS 15/05 - ORD | YATES | 2017-05-16 | 2017-06-29 | Back from PC 26/5 - BOOKED TO INSTALL FRIDAY 16TH. Est27/6. Est 28/6 | 22 |  | 2017-05-30 |  | 2017-06-22 | 2017-05-30 | 2017-06-15 | 2017-05-30 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 |  |  | 8
Coast To Coast - 1181 - 2673 | CL | 2017-06-12: 7 | 16.7 | [6 empty] | CAD, PS 19/5 - ORD | YATES/MET SIL GLO PEARL | 2017-05-25 | STACKER TO WELDING BAY - STU TO APPROVE. Material to PC today 30/5 | 20
Coast To Coast - 1182 - 2617 | CL | 2017-06-12: 2 |  |  |  | 4.6 | [9 empty] | PS 19/5 | CITI PEARL VIV | 2017-05-02 | 2017-06-28 | AD05 TO PCS. Waiting on midrail adaptor 30/5, due in today, JM chase up. Est 31/5. Due in 8/6. Waiting on glass. Est23/6. est 27/6 | 21 |  |  |  | 2017-06-09 |  |  | 2017-05-31 | 2017-06-15 | 2017-06-15 |  |  |  |  | 2
Coast To Coast - 1185 - 2658 | CL | 2017-06-12: 17 |  | 32.9 | [7 empty] | PS 8/5, ORD 9/5 | YATES | 2017-05-19 | 2017-07-11 | Due back from PC this week, JM to update. Push through to end of week 13/6. Allan call Stu do tracks first. Missing finger grip, no eta. Est28/6. Est 29/6 | 10 |  |  | 2017-06-22 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 |  |  | 17
Coast to Coast - 1186 - 2678 | CL | 2017-06-12: 4 |  |  | 8.5 | [8 empty] | PS 22/5 - ORD | YATES/ZEUS WHITE | 2017-05-31 | 2017-07-07 | APPROVED 22/5 | 12 |  |  | 2017-06-08 | 2017-06-05 | 2017-06-05 | 2017-06-05 | [6 empty] | 4
Coast To Coast - 1187 - 2674 | DLi | 2017-06-12: 5 |  |  |  | 9.9 | [9 empty] | PS 19/5 - ORD 22/5 | YATES/LUNAR GREY | 2017-05-25 | 2017-06-30 | APPROVED 22/5. Due back 31/5 from PC. Bit of rework needed. | 24 |  |  |  | 2017-06-20 | 2017-06-20 | 2017-06-20 | [7 empty] | 5
Coast to Coast - 2745 | ext | [14 empty] | ORD YATES 6/6 | Mother of Pearl H Sec | 2017-06-29 | Dli h Section Only | 64 | [6 empty] | 2017-06-07 | [9 empty] | 2017-06-16 | 0
Coast To Coast - Robinson - 2741 | DL | 2017-06-12: 6 |  | 7.7 | [7 empty] | PS 22/6 | PEARL WHITE | 2017-06-26 | 2017-07-12 |  | 14 | [12 empty] | 6
Coastal Blinds Bundy - Bracken 2 - 2811 | Dli | 2017-06-12: 8 |  | 6.7 | [7 empty] | PS 03/07 | CUSTOM BLACK | 2017-07-27 | 2017-07-12 | PUSH THROUGH PLEASE REF MG. JG: Has to be on time. | 22 | [12 empty] | 8
Coastal Blinds Bundy - Pattinson - 2791 | DLi | 2017-06-12: 6 |  |  | 11.3 | [8 empty] | PS 14/6 | PEARL WHITE | 2017-06-21 | 2017-06-26 | URGENT ORDER - ROBYN DID NOT ACTION. Est compl 26/6 | 6 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | [8 empty] | 6
Coastal R/S - 2691
Coastal R/S - 2691 | Dli | 2017-06-12: 4 | 7.3 | [6 empty] | MTO 8/5 - PS 7/6 | KRISTOM/WINDSPRAY | 2017-06-07 | TEST PC ORDER
Cover Me NQ - Bradshaw - 2714 | DLi | 2017-06-12: 3 | 4.8 | [6 empty] | PS 12/6 | PEARL WHITE | 2017-06-17 |  | 35 |  |  |  |  | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | [9 empty] | 3
Cover Me NT - Pearson - 2750 | DLi | 2017-06-12: 10 | 7.1 | [6 empty] | PS 6/6 AF | PEARL WHITE | 2017-06-29
Cover Me Nt - Talbot 2 - 2766 | DLi | [7 empty] | 1 | [6 empty] | PS 19/6 - AF | PEARL WHITE | 2017-06-29 |  | 61 | [7 empty] | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 |  |  |  | 1 | bar: 2017-06-19
Cuchi Interiors - Christian - 2779 | DLi | 2017-06-12: 3 |  | 3.8 | [7 empty] | PS 27/6 | CUSTOM BLACK | 2017-07-06 | 2017-07-11 |  | 20 | [12 empty] | 3
Decor - Kilmartin - 2647
Decor - Kilmartin - 2647 | DLi | 2017-06-12: 10 |  | 40.3 | [5 empty] | MTO 26/5 - PS 9/6 - MTO 2 15/6 | AAF/CLEAR ANO | 2017-06-14 | MTO 2 DONE TO COMPLETE STAGE 3 PANELS 15/6. Supply with 'fair' quality blades only. Est 22/6. | 31 |  | 1 |  |  |  |  | 2017-05-30 | 2017-06-07 | 2017-06-12 | 2017-06-07 | [6 empty] | 2017-06-23 | 10
Decor - Kilmartin - 2647 | DLi | 2017-06-12: 10 |  |  | 40.3 | [8 empty] | MTO 26/5 - PS 9/6 - MTO 2 15/6 - PS26/6 | AAF/CLEAR ANO | 2017-06-14 | 2017-06-30 | MTO 2 DONE TO COMPLETE STAGE 3 PANELS 15/6. Supply with 'fair' quality blades only. Est 22/6. | 34 |  |  |  | 2017-05-30 | 2017-06-07 | 2017-06-12 | 2017-06-07 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 |  |  | 10
EHI - Calderwood - 2778 | DLi | 2017-06-12: 5 |  |  |  | 4.5 | [9 empty] | CAD, PS 8/6 | PEARL WHITE | 2017-06-12 | 2017-06-28 | CUSTOMER ERROR WHEN ORDERED PLEASE PUSH THROUGH. Est13/6. est27/6 | 25 |  |  |  |  | 2017-05-31 | 2017-05-31 | 2017-05-31 |  | 2017-05-31 | 2017-05-31 |  |  |  | 5
EHI Aust - Maconochie - 2802 | DLi | 2017-06-19: 4 |  |  | 2.5 | [6 empty] | PS 04/07 | PEARL WHITE | 2017-07-18 |  |  | 51 | [12 empty] | 4
Genix - Morningside - 2789 NEW CUSTOMER | DLi | 2017-06-12: 5 |  | 5.3 | [7 empty] | PS 03/07 NH | PEARL WHITE | 2017-07-11 | 2017-07-12 |  | 40 | [12 empty] | 5
Geo Shutters - Mulgrew - 2767 | DLi | 2017-06-12: 4 |  |  |  | 3.2 | [9 empty] | PS 19/6 - AF | WOODLAND GREY | 2017-06-30 |  |  | 48 | [13 empty] | 4
Go Blinds - Martin - 2740 | DLi | 2017-06-12: 12 |  |  |  | 10.8 | [9 empty] | PS 21/6 | PEARL WHITE | 2017-06-26 | 2017-06-29 | FLASHINGS FROM P&J, YATES TO PC FLASHINGS. Est 30/6 | 32 | [13 empty] | 12
Gutridge - 11299 RETAIL | CL | 2017-06-12: 3 |  | 6.2 | [7 empty] | PS 14/6 - ORD | YATES/BERRY GREY | 2017-05-31 | 2017-07-11 | DELAY IN MEASURE UP CAUSED BY CLIENT | 12 |  |  | 2017-06-21 | 2017-06-12 | 2017-06-15 | 2017-06-15 | [6 empty] | 3
Impulse - Dunn - 2768 | DLi | 2017-06-12: 3 | 4.2 | [6 empty] | PS 19/6 - AF | PEARL WHITE |  |  |  | 2017-06-30
Impulse - Horniblow - 2759 | DLi | 2017-06-12: 2 |  |  |  | 3.6 | [9 empty] | PS 6/6 CF | PEARL WHITE | 2017-07-01 | 2017-06-30 |  | 53 | [13 empty] | 2
Invisage - Diggins - 2806 | DLi | 2017-06-19: 4 |  |  | 4.3 | [6 empty] | PS 05/07 - AF | WHITE SATIN | 2017-07-20 | 2017-07-12 |  | 53 | [12 empty] | 4
Istyle - Beattie Remake - 2733 | DLi | 2017-06-19: 10 |  | 14.5 | [5 empty] | CAD, PS 26/5 - ORD | YATES/ANOTEC SIL GREY | 2017-06-23 | STACKER PAPERWORK TO WELDING BAY - LAST CHANCE | 48 | [6 empty] | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 |  |  |  |  | 2017-06-15 | 10
Modern Qld - Baldwin - 2676 | DLi | 2017-06-12: 4 | 6.2 | [6 empty] | PS 16/5 | S'MIST & W'GREY | 2017-05-19 | FLASHINGS, BOX & FLATBAR TO YATES. Allan to check & let us know 30/5 | 18 |  | 1 |  |  |  |  | 2017-05-18 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-06 |  |  | 2017-06-06 | 4
Modern Qld - Langbourne - RM2702 | EXT | 2017-06-26: IS THIS GONE??? | [9 empty] | ORDERED 26/6 P&J | PEARL WHITE | URGENT | 2017-07-01 | BOX AND FLASHING NOT ORDERED WHEN PROCESSED | 4
Modern Qld - Lawson - 2797 | EXT | [16 empty] | ORD YATES 19/6 | Paperbark | 2017-06-30 |  | TO BE CUT TO SIZE BEFORE DESPATCH | 30 |  |  | 2017-06-07 | [9 empty] | 0 | bar: 2017-06-12
Modern Qld - Memorey - 2777 | DLi | 2017-06-19: 4 |  |  |  |  | 3.4 | [8 empty] | PS 23/6 | PEARL WHITE | 2017-07-05 |  |  | 59 | [13 empty] | 4
Modern Qld - Newbery - 2770 | DLi | 2017-06-12: 3 |  |  | 3.3 | [8 empty] | PS23/6 | PEARL WHITE | 2017-07-03 | 2017-07-10 |  | 31 | [12 empty] | 3
Modern Qld - Seeto - 2681 | DLi | 2017-06-12: 28 | 48.6 | [6 empty] | CAD, PS 25/5 | CLASSIC CREAM | 2017-05-20 | FLASHINGS FROM P&J, FLASHINGS AND BOC TO YATES. JM to update on PC date 30/5. Est 16/6. Missing 1 Box. Est22/6 | 19 |  | 1 |  |  | 2017-05-31 |  | 2017-06-21 | 2017-06-01 | 2017-06-14 | 2017-06-01 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 |  |  | 2017-06-22 | 28
Modern Qld - Van Veen - 2795 | DLi | 2017-06-12: 4 |  | 5.4 | [7 empty] | PS 03/07 - AF | PEARL WHITE | 2017-07-12 | 2017-07-12 |  | 21 | [12 empty] | 4
Modern Syd - Hollerbranese - 2743 | DLi | 2017-06-26: 8 | [5 empty] | 12.7 | [7 empty] | PS 19/6 - ORD | Yates/Primrose | 2017-07-10 | 2017-06-30 | NO BIFOLD DIRECTION OR MIDRAIL HEIGHT | 66 |  |  |  | 2017-06-22 | [9 empty] | 8
Modern Syd - Lee flashings - 2638 | FLS | [20 empty] | ORD P&J 4/4 | YATES | 2017-05-03 | 2017-06-16 | On the floor 30/5, Waiting on QC. | 9 |  |  |  | 2017-06-07 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-06-06 |  |  | 0 | bar: 2017-06-12
Noosa Screens - Wenck Recto 2 - RM2605-2 | DLi | 2017-06-12: 6 | 11.4 | [6 empty] | PS 15/6 | PEARL WHITE | ASAP | PROMISED FOR 23rd JUNE BY JAN | 2 | FLS | [5 empty] | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | [5 empty] | 2017-06-23 | 6
Qld Blinds - Ironside - Dli 2736 | Dli | 2017-06-12: 16 | 20.3 | [6 empty] | CAD.PS 15/6 | MONUMENT | 2017-06-23 | Need to be on time. Est23/6 | 41 | [16 empty] | 2017-06-23 | 16
Rainbow - Stuart - 2734 | DLi | [8 empty] | 2.4 | [7 empty] | PS 22/6 | YATES/DEEP OCEAN | 2017-07-04 | 2017-07-12 |  | 19 | [12 empty] | 1 | bar: 2017-06-12
S&T Glass - 804 Piermonde - 2613 | CL | 2017-06-12: 20 |  |  |  | 32 | [9 empty] | CAD, PS 4/5 | YATES | 2017-05-02 | 2017-06-21 | REQUIRED ASAP - BENDER COMING 10TH. Need CL frame. Back from PC 30/5. Rework req 6/6. est 16/6. Completed 21/6 | 13 |  |  |  | 2017-06-20 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-20 | 2017-06-21 | 2017-06-20 | 2017-06-20 |  |  | 20
Shade FX - Mandy - 2780 | DLi | 2017-06-12: 6 |  |  | 8.7 | [8 empty] | PS 29/6 | PEARL WHITE | 2017-07-06 | 2017-07-11 |  | 22 | [12 empty] | 6
Shadeview - Brennan - 2752 | DLi | 2017-06-12: 5 |  |  |  | 4.7 | [9 empty] | PS 6/6 AF | PEARL WHITE | 2017-06-30 | 2017-06-29 | est29/6 | 33 |  | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | [7 empty] | 5
Shadeview - Gracey - 2732 | Dli | [10 empty] | 2 | [9 empty] | PS 1/6 AF | PEARL WHITE | 2017-06-23 | 2017-07-03 | est 3/7. Completed 27/6 | 38 |  | 2017-06-15 | 2017-06-15 | 2017-06-15 | [9 empty] | 1 | bar: 2017-06-12
Shadeview - Rupp - 2727 | CL | 2017-06-12: 4 |  |  |  | 11.4 | [9 empty] | PS 13/6 | YATES/Pale Eucalypt | 2017-06-19 | 2017-06-28 | Customer asks for 30/6 in their store. | 28 |  |  |  | 2017-06-22 | [9 empty] | 4
Shadeview - Steel - 2762 | Dli | 2017-06-12: 6 | 6.8 | [6 empty] | PS 19/6 - AF | PEARL WHITE | 2017-06-27 | 2017-07-11
Shutter Tec - Carson - 2790 | DLi | [11 empty] | 1 |  |  | PS 14/6 | PEARL WHITE | 2017-07-12 | URGENT ORDER - SAMPLE FOR POSSIBLE FUTURE ORDERS | 104 | bar: 2017-07-10
Sunjan - Bond - RM2654 | DLi | 2017-06-12: 6 | 1.2 | [6 empty] | PS 5/6 | YATES/MANOR RED | NOW | Est 7/6. Est 23/6 | 4 | CL | [5 empty] | 2017-06-15 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 |  |  | 2017-06-23 | 6
Sunsatate - Juergan Recto - RM2568 | dlI | 2017-06-12: 12 |  | 13 | [5 empty] | PS 5/6 | PEARL WHITE | NOW | Initially est 15/6. Est 22/6 | 3 |  | 1 |  | EXT | [12 empty] | 2017-06-22 | 12
Sunshine - Beasley - 2708
Sunshine - Beasley - 2708 | DLi | 2017-06-12: 8 |  |  | 9.4 | [8 empty] | PS 9/6 | WHITE SATIN | 2017-06-09 | 2017-06-30 | FLASHING FROM P&J - YATES TO PC FLASHING & BOX. Est29/6 | 10 |  |  | 2017-06-20 | 2017-06-14 | 2017-06-14 | 2017-06-14 | [6 empty] | 8
Sunshine - Layham - 2756 | DLi | 2017-06-12: 6 |  |  |  | 17.1 | [9 empty] | PS 6/6 AF | PEARL WHITE | 2017-07-01 | 2017-06-30 | Est 29/6 | 51 | [13 empty] | 6
Sunshine - Mazerolle - 2721 | DLi | 2017-06-12: 5 | 6.7 | [6 empty] | PS 15/6 | PEARL WHITE | 2017-06-19 | BOX TO YATES. Est 22/6 | 34 | [6 empty] | 2017-06-21 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-31 |  | 2017-06-22 | 5
Sunshine - Roelofs - 2757 | DLi | 2017-06-12: 16 |  |  | 46.9 | [8 empty] | CAD 22/6 PS 23/6 | PEARL WHITE | 2017-07-01 | 2017-07-06 |  | 28 | [12 empty] | 16
Sunshine - Rogers - 2758 | Dli | 2017-06-12: 12 |  |  |  | 9.8 | [9 empty] | PS 6/6 AF | PEARL WHITE | 2017-07-01 | 2017-06-21 | Completed 21/6 | 15 |  |  |  | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-21 | 2017-06-21 | 2017-06-21 |  |  | 12
Sunshine - Wheeler - 2742 | DLi | 2017-06-26: 3 |  |  | 3 |  |  |  |  | PS 1/6 AF | CLASSIC CREAM | 2017-06-26 |  | 53 | [17 empty] | 3
Sunstate - Newbury - 2764 | DLi | 2017-06-12: 4 |  |  | 4.9 | [8 empty] | PS 29/3 | PEARL WHITE | 2017-07-07 | 2017-07-11 |  | 23 | [12 empty] | 4
Supaview - Hughes Recto - RM2680 | Dli | 2017-06-12: 7 | 10.88 | [6 empty] | PS 29/5 | CUSTOM BLACK | NOW | Est 8/6. Est22/6 | 3 |  |  |  | DL |  |  | 2017-06-09 | [9 empty] | 2017-06-22 | 7
Supaview - Otte - 2784 | DLi | 2017-06-12: 13 |  |  | 24 | [8 empty] | PS 13/6 | PEARL WHITE | 2017-07-07 | 2017-06-30 | URGENT ORDER - ROBYN DID NOT ACTION | 14 | [12 empty] | 13
Supaview - RSL - 2705
Supaview - RSL - 2705 | Dli | 2017-06-12: 16 | 8.5 | [6 empty] | CAD 7/6 - PS 8/6 | PEARL WHITE | 2017-06-04 | drawings approved 7/6 ps to do | 22 |  |  |  |  | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | [8 empty] | 16
Surf Coast - Pink - 2763 | DLi | 2017-06-12: 8 | 9 | [6 empty] | PS 19/6 - AF | PEARL WHITE | 2017-06-27 |  | 48 | [9 empty] | 2017-06-06 | 2017-06-12 |  | 2017-06-12 | [7 empty] | 8
Tommorows - Price - 2693 | DLi | 2017-06-12: 6 |  |  |  | 13.6 | [9 empty] | PS 31/5 AF | WOODLAND GRY | 2017-06-08 | 2017-06-15 | Returned from PC 6/6. Completed & delivered 15/6 | 8 |  |  | 2017-05-22 | 2017-06-07 | 2017-06-07 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 |  | 6
Tomorrows - Vandermatt - 2738 | DLi | 2017-06-12: 7 |  |  |  | 10.3 | [9 empty] | PS 20/6 - AF | CLASSIC CREAM | 2017-06-25 | 2017-06-28 | Est 27/6. est 3/7. Completed 27/6 | 41 | [13 empty] | 7
U Select - Quazi - 2749 | DLi | 2017-06-12: 4 |  |  |  | 7.7 | [9 empty] | PS 6/6 CF | PEARL WHITE | 2017-06-30 | 2017-06-30 | Est 28/6, Est 29/6 | 30 | [13 empty] | 4
Walker - 11393 RETAIL | CL | 2017-06-12: 10 |  |  |  | 18 | [9 empty] | PS 15/5 - ORD 16/5 | YATES | 2017-05-16 | 2017-06-28 | Back from PC 29/5. Est 16/6. Profile req. Est22/6. Est 26/6. est28/6 | 15 |  |  |  | 2017-06-09 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | [5 empty] | 10
Weatherley - 11394 RETAIL | CL | 2017-06-12: 8 |  | 19.5 | [5 empty] | CAD PS 12/5 - ORD 15/5 | YATES | 2017-05-16 | Back from PC 24/5 - INSTALL WED 21ST. Est 22/6 | 14 |  | 1 |  |  |  |  | 2017-05-30 | 2017-06-06 | 2017-06-06 | 2017-06-06 | [6 empty] | 2017-06-22 | 8
Young - 11388 RETAIL | CL | 2017-06-12: 4 |  |  |  | 7.7 | [9 empty] | PS 15/5 - ORD | YATES | 2017-05-17 | 2017-06-28 | Back from PC 26/5. Prep Error 7/6 mat req. est 16/6. wrong colour. Est 23/6. Est28/6 | 16 |  |  |  | 2017-06-21 | 2017-06-06 | 2017-06-07 | 2017-06-06 | [6 empty] | 4
Bozzy - Whittleton - 2792 | DLi | 2017-06-12: 2 |  | 7.9 | [7 empty] | PS 06/07 - AF - ON STOP | WHITE SATIN | 2017-07-12 |  |  | 44 | [12 empty] | 2
Bozzy Bris - Soeters - 2715 | DLi | 2017-06-12: 8 |  | 7.5 | [7 empty] | PS 1/6 AF | APO Grey | 2017-06-30 | 2017-07-10 |  | 15 |  |  | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | [6 empty] | 8
Holmes 00L11390 - RETAIL | CL | 2017-06-26: AT PC | [9 empty] | NEW STACKER FRAME 26/6 | PCS/ETERNITY SILVER | URGENT | NOW | REP STACKER FRAME | 7
Bozzy - Ventris - 2816 | DLi | 2017-07-03: 9 |  |  |  |  | 2.6 |  |  |  |  | PS 10/7 - AF | SURFMIST | 2017-08-01 | 2017-07-18 |  | 47 | [12 empty] | 0
Bozzy - Hille - 2717 | DLi | 2017-06-12: 21 |  | 31.4 | [7 empty] | PS 29/06 | YATES/Anodic Off White | 2017-06-30 | 2017-07-14 |  | 18 | [12 empty] | 21
Bozzy - Hunt - 2801 | DLi | 2017-06-19: 8 |  |  | 11.4 | [6 empty] | PS 7/7 - ON STOP | CLASSIC CREAM | 2017-07-17 | 2017-07-18 |  | 38 | [12 empty] | 8
Sunstate RS - Newbury 2 - 2830 | DLi | 2017-06-12: 3 |  | 2.9 | [7 empty] | PS 11/7 | PEARL WHITE | 2017-07-14 | 2017-07-11 | PANELS MISSED ON ORIGINAL ORDER - BRETT PROMISED FOR FRIDAY | 14
Bozzy Bris - Zaver - 2788 | DLi | 2017-06-12: 19 | 62 | [6 empty] | PS 5/7 - ON STOP | WHITE SATIN | 2017-07-10 | 2017-07-14 |  | 12 | [12 empty] | 19
Bozzy - Barr 2 - 2783 | DLi | 2017-06-12: 11 | 11.8 | [6 empty] | PS 13/6 | PEARL WHITE | 2017-07-07 | 2017-06-30 | Need to leave by 7/7 | 10 | [12 empty] | 11
Coast to Coast - 1169 - 2502 | DLi | 2017-06-12: 20 | 27 | [6 empty] | PS 28/2 | YATES/RIVERGUM | 2017-03-17 | 2017-07-17 | Not urgent. Est 16/6. Est22/6. Est 3/7 | 14 |  |  |  | 2017-05-30 | 2017-06-01 | 2017-05-30 | 2017-06-13 | 2017-06-21 |  |  |  |  | 20
Coast To Coast - 1180 - 2570 | CL | 2017-06-12: 7 | 14.4 | [6 empty] | CAD, PS 11/4 - ORD 12/4 | YATES/WHITE BIRCH | 2017-04-13 | 2017-06-30 | Paperwork error, more mat req. Est 22/6. est28/6 | 9 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | [5 empty] | 7
Bozzy - Orridge - 2815 | DLi | 2017-06-26: 12 |  |  | 11.3 |  |  |  |  | PS 6/7 AF - ON STOP | WHITE SATIN | 2017-08-01 | 2017-07-18 |  | 20 | [12 empty] | 0
The Shutter Guy - Crosbie - RO1722 | DLi | 2017-06-19: IS THIS GONE??? | [7 empty] | PAPERWORK 21/6 | PEARL WHITE | 2017-06-01 | 2017-07-01 | PILE, BOOKER RODS AND RIVETS | 1
Supaview - Frawley - 2787 | DLi | 2017-06-12: 3 | 3.4 | [6 empty] | PS 03/07 - AF | PEARL WHITE | 2017-07-10 |  |  | 32 |  |  | 2017-06-07 | [9 empty] | 3
Shade FX - Headrick - 2747 | DLi | 2017-06-12: 3 | 3.8 | [6 empty] | PS 03/07- NH | Elmos Fire | 2017-07-10 |  |  | 33 | [12 empty] | 3
Boardwalk - Martin - 2769 | DLi | 2017-06-12: 7 | 14.1 | [6 empty] | CAD, PS 26/6 | SURFMIST | 2017-07-03 |  |  | 28 | [12 empty] | 7
Bozzy - Reynolds - 2793 | DLi | 2017-06-12: 16 | 22.3 | [6 empty] | PS 06/07 - AF - ON STOP | PEARL WHITE | 2017-07-12 | 2017-07-18 |  | 18 | [12 empty] | 16
Modern Qld - Schmidt - 2794 | DLi | 2017-06-12: 5 | 4.8 | [6 empty] | PS 27/6 AF | SURFMIST | 2017-07-12 |  |  | 35 | [12 empty] | 5
Modern Qld - Memorey - 2772 | DLi | 2017-06-12: 4 | 3.6 | [6 empty] | PS 26/6 - ORD 27/6 | PEARL WHITE | 2017-07-03 | 2017-07-14 | HAWTHORNE GREEN BOX AND FLASHINGS TO YATES | 11 | [12 empty] | 4
Central Coast RS - Chapman - 2822 | DLi | 2017-06-26: 4 |  |  | 5 |  |  |  |  | PS 11/7 - NH | WHITE SATIN | 2017-08-01 |  |  | 45 | [12 empty] | 0
EHI - 92092 - 2833 | DLi | 2017-06-26: 2 |  |  | 3.6 |  |  |  |  | PS 13/7 | YATES/Charcoal Satin | 2017-08-01 |  | SUPER URGENT FAST TURN AROUND PROMISED TO CUSTOMER | 49 | [12 empty] | 0
Blindo - Greer Rd - 2829 | DLi | 2017-06-26: 4 |  |  | 4.3 |  |  |  |  | PS 10/7 - AF | PEARL WHITE | 2017-08-04 |  |  | 58 | [12 empty] | 0
Modern Syd - Hill - 2755 | DLi | 2017-06-12: 3 | 7.9 | [6 empty] | CAD, PS | YATES+WHITE SATIN STK | 2017-06-30 | 2017-07-21 | 150 PROFILE TO YATES REST STOCK | 21 | [12 empty] | 3
McCully Blinds - Showroom - 2823 | DLi | [9 empty] | 1.8 |  |  |  |  | PS 10/7 - AF | PEARL WHITE | 2017-08-02 |  | NEW CUSTOMER! | 53 | [12 empty] | 0 | bar: 2017-06-26
Cover Me NQ - Campbell - 2781 | DLi | 2017-06-12: 11 | 6.5 | [6 empty] | CAD, PS 30/6 | PEARL WHITE | 2017-07-06 | 2017-07-17 |  | 15 | [12 empty] | 11
Boardwalk - Guy - 2812 | Dli | 2017-06-19: 8 |  | 10.2 | [5 empty] | CAD, PS 11/7 | PEARL WHITE | 2017-07-27 |  |  | 42 | [12 empty] | 8
Modern Syd - Han - 2796 | DLi | 2017-06-12: 8 | 15.9 | [6 empty] | PS 10/7 | CLASSIC CREAM | 2017-07-14 | 2017-07-18 | L FRAME AND AS8c SENT TO YATES | 19 | [12 empty] | 8
Sunshine - Schmidt - 2754 | DLi | 2017-06-12: 4 | 6.4 | [6 empty] | PS 03/07 | YATES/Paperbark | 2017-07-12 |  |  | 34 | [12 empty] | 4
Grand Total |  | 791 | 93 | 36 | 9 | 1 | 0 | 0 | 431.98 | 290.4 | 221.6 | 354.3 | 9 | 12.7 | 0 | WHOLESALE/RETAIL JOBS |  |  | 49
Sq Mtrs |  | 431.98 | 290.4 | 221.6 | 354.3 | 9 | 12.7 | 0
[16 empty] | PANELS |  |  | 920
Commercial Panels |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Commercial SQM |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [7 empty] | SQUARE METRES |  |  | 943.98
Domestic Panels |  | 791 | 93 | 36 | 9 | 1 | 0 | 0 | [7 empty] | COMMERCIAL JOBS |  |  | 0
Domestic SQM |  | 431.98 | 290.4 | 221.6 | 354.3 | 9 | 12.7 | 0

## Weekly Units
WEEK OF | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04
| 6 |  |  | 14 | 8 | 7
| 3 |  |  | 2 | 8 | 2
| 13 |  |  | 2 | 10 | 4
| 9 |  |  | 9 | 4 | 4
| 2 |  |  | 6 | 6
| 20 |  |  | 2 | 6
| 11 |  |  | 10 | 6
| 2 |  |  | 10 | 4
| 20 |  |  | 2 | 6
| 10 |  |  |  | 14
| 16 |  |  |  | 12
| 6 |  |  |  | 2
| 2 |  |  |  | 1
| 3 |  |  |  | 4
| 13 |  |  |  | 16
| 6 |  |  |  | 7
| 2 |  |  |  | 2
2
6
2
TOTAL | 154 | 0 | 0 | 57 | 116 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0